## Product Backlog
Epic | User Story Title | Story | Acceptance Criteria | Priority | Sprint | Status
Authentication | User Login | As a user, I want to login to the system so I can use the software | 1) Given the user enters a valid username and password → When clicking “Login” → Then the system grants access 2) If credentials are invalid, an error message is displayed 3) Successful login redirects to the main dashboard | Medium | Sprint 1 | To do
User Profile | User personal profile view | As a user, I want to view my personal profile so I can see my information | 1)Given the user is logged in → When they click “Profile” → Then the system displays their name, ID, and classroom 2) The information must be accurate and up to date | High | Sprint 1 | To do
Course Management | Course CRUD | As an admin, I want to manage courses so that I can add, update, or delete course data | 1) Admin can add, edit, delete, and view courses 2) The system validates required fields 3) After successful operation, the course list updates immediately | High | Sprint 2 | To do
Registration | Course Registration | As a student, I want to register for course so I can attend it | 1) Student can view the available courses 2) When selecting a course → the system registers it under their name 3) Prevents duplicate registration or full-class enrollments | High | Sprint 2 | To do
Classroom management | Classroom CRUD | As a an admin, I want to manage classrooms to organize students effectively | 1) Admin can add, edit, delete, and view classrooms 2) Each classroom contains a list of students 3) The system validates classroom name and capacity | Medium | Sprint 3 | To do
Student Management | Student CRUD | As an admin, I want to manage students so I can keep student data updated | 1) Admin can add, edit, delete, and view student information 2) Each student must belong to one classroom 3) The system validates ID uniqueness | High | Sprint 3 | To do
System Optimization | Testing & UI Improvement | As a developer, I want to test and improve the UI so the system is stable and user-friendly | 1) Run functional and unit testing on all CRUD features 2) Fix detected bugs and retest 3) Adjust UI layout for clarity and responsive design | Medium | Sprint 4 | To do
User Management | Manage Users | As an admin, I want to manage all users so I can control system access | 1) Admin can create, update, deactivate, or delete user accounts 2) The system validates username uniqueness 3) Deactivated users cannot log in | High | Sprint 4 | To do